## Sheet1
| 2016-10-20 | 2016-10-25 | 2016-11-01 | 2016-11-10 | 2016-11-15 | 2016-11-17 | 2016-11-29 | 2016-12-01 | 2016-12-02 | 2016-12-03 | 2016-12-04
The team | Brain Storming | Find method to write the app | Design the game detail | Write the code | Finish design work | Finish the core code | Optimize the code | Draw user interface | Optimize user experience | Test and finsh coding | Prepare for the presentation
Paper work | 2016-10-20: Finish the proposal; 2016-10-25: Prepare for final report; 2016-11-15: Write final report; 2016-12-03: PPT, Poster
Code | 2016-10-25: Choose to use Unity in coding; 2016-11-01: Write the code; 2016-11-17: Debug; 2016-11-29: Add more function; 2016-12-02: Optimize user experience; 2016-12-03: Test
Design | 2016-10-25: Design the game detail; 2016-11-15: Optimize the design; 2016-12-01: Draw user interface; 2016-12-03: Test
1, Dongyang Hu
2, Suyi Diao
3, Tianchi Wu
4, Simeng Zhao
1,2,3,4
1
2,3
4